## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours
SRS | write SRS for Login feature and maintain RTM | Youstina Atef | 3 | 3
| write SRS for Registration feature and maintain RTM | Youstina Atef | 3 | 3
| write SRS for Client feature and maintain RTM | Rana Saad | 4 | 3
| write SRS for Supplier feature and maintain RTM | Muhamed Mumtaz | 4 | 5
| Review for Login feature SRS | Rana Saad | 1 | 3
| Review for Registration feature SRS | Mariam Abdelmoneim | 1.5 | 2
| Review for Client feature SRS | Abdallah El-Karamany | 1 | 1
| Review for Supplier feature SRS | Mariam Abdelmoneim | 1.5 | 1
Test cases | Write test cases for Login feature SRS and maintain RTM | Abdallah El-Karamany | 3 | 2
| Write test cases for Registration feature SRS and maintain RTM | Rana Saad | 3 | 3
| Write test cases for Client feature SRS and maintain RTM | Youstina Atef | 3 | 3
| Write test cases for Supplier feature SRS and maintain RTM | Mariam Abdelmoneim | 4 | 2
| Review test cases for Login feature | Muhamed Mumtaz | 4 | 3
| Review test cases for Registration feature | Mariam Abdelmoneim | 1 | 1
| Review test cases for Client feature | Rana Saad | 1 | 1
| Review test cases for Supplier feature | youstina Atef | 1 | 1
UI Design | Sketch UI Design for Login page | Rana Saad | 4 | 4
| Sketch UI Design for Registration page | Youstina Atef | 3 | 4
| Sketch UI Design for Home page | Abdallah El-Karamany | 5 | 7
| Sketch UI Design for Cart page | Mariam Abdelmoneim | 3 | 3
| Sketch UI Design for checkout page | Muhamed Mumtaz | 4 | 5
| Sketch UI Design for Order History page | Mariam Abdelmoneim | 4 | 3
| Sketch UI Design for Supplier to add new product | Abdallah El-Karamany | 4 | 5
| Review UI Design for Supplier to add new product | youstina Atef | 1 | 1
| Review UI Design for Login page | Muhamed Mumtaz | 1 | 1
| Review UI Design for Registration page | Mariam Abdelmoneim | 1 | 1
| Review UI Design for Home page | Youstina Atef | 1 | 1
| Review UI Design for Cart page | Abdallah El-Karamany | 1 | 1
| Review UI Design for checkout page | Rana Saad | 1 | 1
| Review UI Design for Order History page | Abdallah El-Karamany | 1 | 0.5
Release 1 Comments | Update PMP according to comments | Abdallah El-Karamany | 3 | 2.5
| Update Risk Register according to comments | Abdallah El-Karamany | 2 | 1
| Create CIL | Abdallah El-Karamany | 1 | 1
| Update CRS Document according to comments | Abdallah El-Karamany | 1 | 1
Release 3 Planning | plan for Release 3 | Abdallah El-Karamany | 2 | 4

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 20 | 22 | 26
Mohamed Mumtaz | 14 | 13 | 14
Youstina Atef | 19 | 14 | 16
Rana Saad | 14 | 14 | 15
Mariam Abdelmoneim | 16 | 16 | 13
Total | 83 | 79 | 84