## Sheet1
ID | comment | SIQ ID
SIQ_Login_001 | is that client can login? | SRS_Login_001
SIQ_Login_002 | Missing what happens if something goes wrong (enter wrong username or wrong password or both) | SRS_Login_001
SIQ_Register_001 | Is the username required to be unique? | SRS_Reg_001
SIQ_Register_002 | Is the email validated using correct format? | SRS_Reg_001
SIQ_Register_003 | Can username contain special characters, or is it strictly letters only? | SRS_Reg_002
SIQ_Register_004 | Is there a specific message when address exceeds 40 characters? | SRS_Reg_003
SIQ_Register_005 | What happens if the user enters a duplicate phone number? | SRS_Reg_004
SIQ_Register_006 | Is there a confirm password field to verify the password? | SRS_Reg_005
SIQ_Register_007 | What happens if the email is already registered? | SRS_Reg_005
SIQ_Register_008 | Is the password required to contain special characters, numbers, or uppercase letters, or only 8-character minimum? | SRS_Reg_006
SIQ_Register_009 | What happens when national ID is less or more than 14 digits? | SRS_Reg_007
SIQ_Register_010 | Is a general error message shown when only one field is invalid? | SRS_Reg_007
SIQ_Register_011 | After successful registration, is the user redirected to a specific page?
SIQ Review_Supplier_001 | Product Id follow ID convention | CRS SIQ_Supplier_001
SIQ Review_Supplier_002 | is the all the product data is mandatory whan adding a product or there is some optional data | CRS SIQ_Supplier_001
SIQ Review_Supplier_003 | what happens if the supplier eneter product Id that is not correct | CRS SIQ_Supplier_002
SIQ Review_Admin_001 | what is the Roles and Responsibilties of the Admin | CRS SIQ_Admin
SIQ Review_Client_001 | payment method is only cash? | CRS SIQ_Cl_005