## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
Test Case Execution | Test Case Execution for Registration Feature | Mariam | 2 | 2 | Done
| Test Case Execution for Login Feature | Rana | 2 | 2 | Done
| Test Case Execution for Supplier Feature | Youstina | 2 | 2 | Done
| Test Case Execution for Client Feature | Muhamed | 2 | 2 | Done
Release 5 Comments | Review and Update Registration feature | Mariam |  |  | To do
| Review and Update Login feature | Rana |  |  | To do
| Review and Update Supplier feature | Youstina |  |  | To do
| Review and Update Client feature | Muhamed |  |  | To do
PM Task | Test Strategy | Abdallah |  |  | To do
Release 6 Planning |  | Abdallah El-Karamany | 3 |  | To do
Overall release % of work Status |  | Total Tasks | 10 | Tasks in % | Total Time Spent
|  | Doing | 0 | 0% | 8
|  | To do | 6 | 60%
|  | Done | 4 | 40%

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 15 | 3 | 0
Mohamed Mumtaz | 10 | 2 | 2
Youstina Atef | 10 | 2 | 2
Rana Saad | 10 | 2 | 2
Mariam Abdelmoneim | 10 | 2 | 2
Total | 55 | 11 | 8