## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
Test Case Execution | Test Case Execution for Registration Feature | Mariam | 2 | 1.5 | Done
| Test Case Execution for Login Feature | Rana |  |  | To do
| Test Case Execution for Supplier Feature | Youstina |  |  | To do
| Test Case Execution for Client Feature | Muhamed |  |  | To do
Release 5 Comments
Release 6 Planning |  | Abdallah El-Karamany | 3 |  | To do
Overall release % of work Status |  | Total Tasks | 5 | Tasks in % | Total Time Spent
|  | Doing | 0 | 0% | 1.5
|  | To do | 4 | 80%
|  | Done | 1 | 20%

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 15 | 3 | 0
Mohamed Mumtaz | 14 | 0 | 0
Youstina Atef | 16 | 0 | 0
Rana Saad | 16 | 0 | 0
Mariam Abdelmoneim | 15 | 2 | 1.5
Total | 76 | 5 | 1.5