## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
UI Design | Create UI Design for Registration page | Youstina Atef | 1 | 1 | Done
| Create UI Design for Login page | Youstina Atef | 1 | 1 | Done
| Create UI Design for Client Home Page page | Rana Saad | 1 | 1 | Done
| Create UI Design for Cart page | Mariam Abdelmoneam | 1 | 0.75 | Done
| Create UI Design for CheckOut page | Rana Saad | 1 | 1 | Done
| Create UI Design for OrderHistory page | Mariam Abdelmoneam | 1 | 0.75 | Done
| Create UI Design for Supplier Home page | Muhamed Mumtaz | 2 | 2 | Done
| Create UI Design for Supplier add new product page | Abdallah El-Karamany | 1 | 1 | Done
| Create UI Design for Supplier Update Product page | Muhamed Mumatz | 2 | 2 | Done
| Create UI Design for Supplier Delete product | Abdallah El-Karamany | 1 | 1 | Done
| Review UI Design for Registration page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review UI Design for Login page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review UI Design for Client Home Page page | Muhamed Mumatz | 0.5 | 0.5 | Done
| Review UI Design for Cart page | Youstina Atef | 1 | 1 | Done
| Review UI Design for CheckOut page | Muhamed Mumatz | 0.5 | 0.5 | Done
| Review UI Design for OrderHistory page | Youstina Atef | 1 | 3 | Done
| Review UI Design for Supplier Home page | Abdallah El-Karamany | 0.5 | 0.5 | Done
| Review UI Design for Supplier add new product page | Rana Saad | 0.5 | 0.5 | Done
| Review UI Design for Supplier Update Product page | Abdallah El-Karamany | 0.5 | 0.5 | Done
| Review UI Design for Supplier Delete product | Rana Saad | 0.5 | 0.5 | Done
System Design | Create System Design for Registration page | Youstina Atef | 4 | 4 | Done
| Create System Design for Login page | Youstina Atef | 4 | 6 | Done
| Create System Design for Client Home Page page | Rana Saad | 2.5 | 3 | Done
| Create System Design for Cart page | Mariam Abdelmoneam | 2 | 2 | Done
| Create System Design for CheckOut page | Rana Saad | 2.5 | 3 | Done
| Create System Design for OrderHistory page | Mariam Abdelmoneam | 2 | 2 | Done
| Create System Design for Supplier Home page | Muhamed Mumtaz | 3 | 3 | Done
| Create System Design for Supplier add new product page | Abdallah El-Karamany | 3 | 3 | Done
| Create System Design for Supplier Update Product page | Muhamed Mumatz | 3 | 3 | Done
| Create System Design for Supplier Delete product | Abdallah El-Karamany | 3 | 3 | Done
| Review System Design for Registration page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review System Design for Login page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review System Design for Client Home Page page | Muhamed Mumatz | 0.5 | 0.5 | Done
| Review System Design for Cart page | Youstina Atef | 1 | 1 | Done
| Review System Design for CheckOut page | Muhamed Mumatz | 0.5 | 0.5 | Done
| Review System Design for OrderHistory page | Youstina Atef | 1 | 1 | Done
| Review System Design for Supplier Home page | Abdallah El-Karamany | 1 | 1 | Done
| Review System Design for Supplier add new product page | Rana Saad | 1 | 1 | Done
| Review System Design for Supplier Update Product page | Abdallah El-Karamany | 1 | 1 | Done
| Review System Design for Supplier Delete product | Rana Saad | 1 | 1 | Done
Release 2 Comments | Review Client SRS, TC and RTM | Youstina Atef | 2 | 2 | Done
| Review Supplier SRS, TC and RTM | Mariam Abdelmoneam | 1 | 1.15 | Done
| Review Registration SRS, TC and RTM | Mariam Abdelmoneam | 1 | 1.15 | Done
| Review login SRS, TC and RTM | Abdallah El-Karamany | 1 | 1 | Done
Release 4 Planning |  | Abdallah El-Karamany | 3 | 3 | Done
Overall release % of work Status |  | Total Tasks | 45 | Tasks in % | Total Time Spent
|  | Doing | 0 | 0% | 67.8
|  | To do | 0 | 0%
|  | Done | 45 | 100%

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 15 | 15 | 15
Mohamed Mumtaz | 12 | 12 | 12
Youstina Atef | 14 | 16 | 20
Rana Saad | 10 | 10 | 11
Mariam Abdelmoneim | 10 | 10 | 9.8
Total | 61 | 63 | 67.8