## Sheet1
Risk ID | Risk Summary | Risk Category | Impact | Likehood | Risk Level | Mitigation Type | Mitigation Plan | Contingency Plan | Owner
R001 | The project team currently consists of only five members, while the planned and optimal team size is six. Operating with fewer team members may result in workload imbalances, slower progress, missed deadlines, reduced quality of deliverables, and increased stress or burnout for existing team members. | Project Risk | Medium | High | High | Mitigate | Request resource from management with skills to match the project domain Distribute workload temporarily among current team members -Additional work hours beyond the standard schedule |  | Project Manager
R002 | One or more team members may take scheduled leave during the project lifecycle. While planned, such absences can still impact timelines and deliverables | Project Risk | Medium | Medium | Medium | Mitigate | Review project schedule and adjust task deadlines for the team member who wants to take a leave. - Extend working hours or work on weekends to compensate. - Request additional support from other teams or departments. |  | Project Manager
R003 | The project currently has zero budget allocated for purchasing a domain name and hosting services required for website deployment. | Product Risk | High | High | High | Mitigate | Use alternative which would be free(GitHub). Take advantage of promotions and discounts. Consider registering a domain for a longer period to reduce cost. explore free subdomains for initial testing. Try to use college email to get free servers for hosting. |  | Project Manager
R004 | The website may be exposed to cyber-attacks such as SQL injection, cross-site scripting (XSS), or brute-force attacks due to insufficient security measures during development and deployment. | Product Risk | High | Medium | High | Mitigate |  | Apply proper authentication, authorization, and password policies | Project Manager
R005 | Team members may lack sufficient training or familiarity with the tools, or technologies required for the successful execution of the project. | Project Risk | Medium | Medium | Medium | Mitigate | Provide targeted training sessions or workshops Assign less experienced members with skilled ones |  | Project Manager