## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
FrontEnd Development | Create FrontEnd for Registration page | Youstina Atef | 3 |  | To do
| Create FrontEnd for Login page | Youstina Atef | 3 |  | To do
| Create FrontEnd for Client Home Page page | Rana Saad |  |  | To do
| Create FrontEnd for Cart page | Mariam Abdelmoneam |  |  | To do
| Create FrontEnd for CheckOut page | Rana Saad |  |  | To do
| Create FrontEnd for OrderHistory page | Mariam Abdelmoneam |  |  | To do
| Create FrontEnd for Supplier Home page | Muhamed Mumtaz | 2 |  | To do
| Create FrontEnd for Supplier add new product page | Abdallah El-Karamany | 1 | 1 | Done
| Create FrontEnd for Supplier Update Product page | Muhamed Mumatz | 2 |  | To do
| Create FrontEnd for Supplier Delete product | Abdallah El-Karamany | 1 | 1 | Done
| Review FrontEnd for Registration page | Mariam Abdelmoneam |  |  | To do
| Review FrontEnd for Login page | Mariam Abdelmoneam |  |  | To do
| Review FrontEnd for Client Home Page page | Muhamed Mumatz | 1 |  | To do
| Review FrontEnd for Cart page | Youstina Atef | 1 |  | To do
| Review FrontEnd for CheckOut page | Muhamed Mumatz | 1 |  | To do
| Review FrontEnd for OrderHistory page | Youstina Atef | 1 |  | To do
| Review FrontEnd for Supplier Home page | Abdallah El-Karamany | 0.5 |  | To do
| Review FrontEnd for Supplier add new product page | Rana Saad |  |  | To do
| Review FrontEnd for Supplier Update Product page | Abdallah El-Karamany | 0.5 |  | To do
| Review FrontEnd for Supplier Delete product | Rana Saad |  |  | To do
BackEnd Development | Create BackEnd for Registration page | Youstina Atef | 3 |  | To do
| Create BackEnd for Login page | Youstina Atef | 3 |  | To do
| Create BackEnd for Client Home Page page | Rana Saad |  |  | To do
| Create BackEnd for Cart page | Mariam Abdelmoneam |  |  | To do
| Create BackEnd for CheckOut page | Rana Saad |  |  | To do
| Create BackEnd for OrderHistory page | Mariam Abdelmoneam |  |  | To do
| Create BackEnd for Supplier Home page | Muhamed Mumtaz | 3 |  | To do
| Create BackEnd for Supplier add new product page | Abdallah El-Karamany | 3 |  | To do
| Create BackEnd for Supplier Update Product page | Muhamed Mumatz | 3 |  | To do
| Create BackEnd for Supplier Delete product | Abdallah El-Karamany | 3 |  | To do
| Review BackEnd for Registration page | Mariam Abdelmoneam |  |  | To do
| Review BackEnd for Login page | Mariam Abdelmoneam |  |  | To do
| Review BackEnd for Client Home Page page | Muhamed Mumatz | 1 |  | To do
| Review BackEnd for Cart page | Youstina Atef | 1 |  | To do
| Review BackEnd for CheckOut page | Muhamed Mumatz | 1 |  | To do
| Review BackEnd for OrderHistory page | Youstina Atef | 1 |  | To do
| Review BackEnd for Supplier Home page | Abdallah El-Karamany | 1 |  | To do
| Review BackEnd for Supplier add new product page | Rana Saad |  |  | To do
| Review BackEnd for Supplier Update Product page | Abdallah El-Karamany | 1 |  | To do
| Review BackEnd for Supplier Delete product | Rana Saad |  |  | To do
Release 3 Comments
Release 4 Planning |  | Abdallah El-Karamany | 3 |  | To do
Overall release % of work Status |  | Total Tasks | 41 | Tasks in % | Total Time Spent
|  | Doing |  | 0% | 2
|  | To do | 41 | 100%
|  | Done |  | 0%

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 15 | 14 | 2
Mohamed Mumtaz | 14 | 14 | 0
Youstina Atef | 16 | 16 | 0
Rana Saad |  | 0 | 0
Mariam Abdelmoneim |  | 0 | 0
Total | 45 | 44 | 2