## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
FrontEnd Development | Create FrontEnd for Registration page | Youstina Atef | 3 | 3 | Done
| Create FrontEnd for Login page | Youstina Atef | 3 | 3 | Done
| Create FrontEnd for Client Home Page page | Rana Saad | 2 | 2 | Done
| Create FrontEnd for Cart page | Mariam Abdelmoneam | 2 | 2 | Done
| Create FrontEnd for CheckOut page | Rana Saad | 2 |  | To do
| Create FrontEnd for OrderHistory page | Mariam Abdelmoneam | 2 | 2 | Done
| Create FrontEnd for Supplier Home page | Muhamed Mumtaz | 2 | 2 | Done
| Create FrontEnd for Supplier add new product page | Abdallah El-Karamany | 1 | 1 | Done
| Create FrontEnd for Supplier Update Product page | Muhamed Mumatz | 2 | 2 | Done
| Create FrontEnd for Supplier Delete product | Abdallah El-Karamany | 1 | 1 | Done
| Review FrontEnd for Registration page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review FrontEnd for Login page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review FrontEnd for Client Home Page page | Muhamed Mumatz | 1 | 1 | Done
| Review FrontEnd for Cart page | Youstina Atef | 1 |  | To do
| Review FrontEnd for CheckOut page | Muhamed Mumatz | 1 |  | To do
| Review FrontEnd for OrderHistory page | Youstina Atef | 1 |  | To do
| Review FrontEnd for Supplier Home page | Abdallah El-Karamany | 0.5 | 0.5 | Done
| Review FrontEnd for Supplier add new product page | Rana Saad | 1 | 1 | Done
| Review FrontEnd for Supplier Update Product page | Abdallah El-Karamany | 0.5 | 0.5 | Done
| Review FrontEnd for Supplier Delete product | Rana Saad | 1 | 1 | Done
BackEnd Development | Create BackEnd for Registration page | Youstina Atef | 3 | 3 | Done
| Create BackEnd for Login page | Youstina Atef | 3 | 3 | Done
| Create BackEnd for Client Home Page page | Rana Saad | 4 | 5 | Done
| Create BackEnd for Cart page | Mariam Abdelmoneam | 4 | 4 | Done
| Create BackEnd for CheckOut page | Rana Saad | 4 |  | To do
| Create BackEnd for OrderHistory page | Mariam Abdelmoneam | 4 |  | Doing
| Create BackEnd for Supplier Home page | Muhamed Mumtaz | 3 | 3 | Done
| Create BackEnd for Supplier add new product page | Abdallah El-Karamany | 3 | 3 | Done
| Create BackEnd for Supplier Update Product page | Muhamed Mumatz | 3 | 3 | Done
| Create BackEnd for Supplier Delete product | Abdallah El-Karamany | 3 | 3 | Done
| Review BackEnd for Registration page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review BackEnd for Login page | Mariam Abdelmoneam | 0.5 | 0.5 | Done
| Review BackEnd for Client Home Page page | Muhamed Mumatz | 1 | 1 | Done
| Review BackEnd for Cart page | Youstina Atef | 1 |  | To do
| Review BackEnd for CheckOut page | Muhamed Mumatz | 1 |  | To do
| Review BackEnd for OrderHistory page | Youstina Atef | 1 |  | To do
| Review BackEnd for Supplier Home page | Abdallah El-Karamany | 1 | 0.5 | Done
| Review BackEnd for Supplier add new product page | Rana Saad | 1 | 1 | Done
| Review BackEnd for Supplier Update Product page | Abdallah El-Karamany | 1 | 0.5 | Done
| Review BackEnd for Supplier Delete product | Rana Saad | 1 | 1 | Done
Release 4 Comments
Release 5 Planning |  | Abdallah El-Karamany | 3 |  | To do
Overall release % of work Status |  | Total Tasks | 41 | Tasks in % | Total Time Spent
|  | Doing | 1 | 2.439% | 55
|  | To do | 9 | 21.95%
|  | Done | 31 | 75.61%

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 15 | 14 | 10
Mohamed Mumtaz | 14 | 14 | 12
Youstina Atef | 16 | 16 | 12
Rana Saad | 14 | 16 | 11
Mariam Abdelmoneim | 15 | 14 | 10
Total | 74 | 74 | 55