## Sheet1
ID | Date | File Name | Reviewer | comment | SIQ ID | Status | Explaination | Document Version
CRS-SIQ Document Review
Review_Login_001 | 2025-04-06 | CRS-SIQ File | Youstina | is that only client can login? | CRS-SIQ_Login_001 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Login_002 | 2025-04-06 | CRS-SIQ File | Youstina | Missing what happens if something goes wrong (enter wrong username or wrong password or both) | CRS-SIQ_Login_001 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_001 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Is the username required to be unique? | CRS-SIQ_Reg_001 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_002 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Is the email validated using correct format? | CRS-SIQ_Reg_001 | Rejected |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_003 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Can username contain special characters, or is it strictly letters only? | CRS-SIQ_Reg_002 | Rejected |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_004 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Is there a specific message when address exceeds 40 characters? | CRS-SIQ_Reg_003 | Rejected |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_005 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | can the user enters a same phone number for multi accounts? | CRS-SIQ_Reg_004 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_006 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Is there a confirm password field to verify the password? | CRS-SIQ_Reg_005 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_007 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | can the user enters a same email for multi accounts? | CRS-SIQ_Reg_005 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_008 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Is the password required to contain special characters, numbers, or uppercase letters, or only 8-character minimum? | CRS-SIQ_Reg_006 | Rejected |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_009 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | What happens when national ID is less or more than 14 digits? | CRS-SIQ_Reg_007 | Rejected |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_010 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | Is a general error message shown when only one field is invalid? | CRS-SIQ_Reg_007 | Rejected |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Register_011 | 2025-04-06 | CRS-SIQ File | Mariam Abdelmoneim | After successful registration, is the user redirected to a Home Page? |  | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Supplier_001 | 2025-04-06 | CRS-SIQ File | Abdallah El-Karamany | Product Id follow ID convention | CRS-SIQ_Supplier_001 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Supplier_002 | 2025-04-06 | CRS-SIQ File | Abdallah El-Karamany | is the all the product data is mandatory whan adding a product or there is some optional data | CRS-SIQ_Supplier_001 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Supplier_003 | 2025-04-06 | CRS-SIQ File | Abdallah El-Karamany | what happens if the supplier eneter product Id that is not correct | CRS-SIQ_Supplier_002 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
Review_Client_001 | 2025-04-06 | CRS-SIQ File | Rana Saad | payment method is only cash? | CRS-SIQ_Cl_005 | Approved |  | 8d3a823e3639a6f40b6cf7bbae1d2c7eddb17b8f
CRS Document Review
Review_Client_001 | 2025-04-09 | CRS File | Youstina | What mean by modify product count ? | CRS_Client_006 | Approved | user can increment or decrement product count | 1971f83128b5ef307b3bcb8d265fd810d81a6946
Review_Login_001 | 2025-04-09 | CRS File | Youstina | What is the error message? | CRS_Login_003 | Approved |  | 1971f83128b5ef307b3bcb8d265fd810d81a6946
Review_Supplier_001 | 2025-04-09 | CRS File | Muhamed Mumtaz | what is product platform? | CRS_supplier_001 | Approved | Add product platform | 1971f83128b5ef307b3bcb8d265fd810d81a6946
Review_Supplier_002 | 2025-04-09 | CRS File | Muhamed Mumtaz | In naming convention why we add color? | CRS_supplier_004 | Approved | remove color from naming convention | 1971f83128b5ef307b3bcb8d265fd810d81a6946
Review_Suplier_003 | 2025-04-09 | CRS File | Muhamed Mumtaz | Is product photo is mandatory or optional | CRS_supplier_005 | Approved | add product photo to be mandatory | 1971f83128b5ef307b3bcb8d265fd810d81a6946
Review_Reg_001 | 2025-04-09 | CRS File | Rana Saad | No registration Gaps | CRS_Reg | Approved |  | 1971f83128b5ef307b3bcb8d265fd810d81a6946
SRS Document Review
Review_Client_001 | 2025-04-15 | SRS File | Abdallah El-Karamany | what if the product is out of stock | SRS_Client_005 | Approved |  | 660008384a6474675cba117bbecaff44211bdc17
Review_Client_002 | 2025-04-15 | SRS File | Abdallah El-Karamany | the client can cancel the order when in the payment page or only complete the process | SRS_Client_010 | Approved | yes the client can also cancel payment | 660008384a6474675cba117bbecaff44211bdc17
Review_Reg_001 | 2025-04-20 | SRS File | Mariam Abdelmoneim | No Gaps | SRS_Reg | Approved |  | 99596a638833117dc9aaeabd36148c6441c9716f
Review_Supplier_001 | 2025-04-20 | SRS File | Mariam Abdelmoneim | No Gaps | SRS_Supplier | Approved |  | 99596a638833117dc9aaeabd36148c6441c9716f
Test Cases Document Review
Review_TC_Login_001 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_001 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_002 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_002 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_003 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_003 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_004 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_004 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_005 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_005 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_006 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_006 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_007 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_007 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_008 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_008 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_009 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_009 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_010 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_010 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_011 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_011 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_012 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_012 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_013 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_013 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Login_014 | 2025-04-19 | Test file | Mohamed Mumtaz | No Gaps | TC_Login_014 | Approved |  | ef50fe1c29fc02acea2f17e5b98048c5c9a592a1
Review_TC_Supplier_001 | 2025-04-21 | Test file | Youstina | in requirements can update product data using product id | TC_Supplier_007 | Approved |  | bab26f49a2a2f340b887e2f69bb084e55dd80040
Review_TC_Supplier_002 | 2025-04-21 | Test file | Youstina | in requirements can delete product data using product id | TC_Supplier_008 | Approved |  | bab26f49a2a2f340b887e2f69bb084e55dd80040