## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
SRS | write SRS for Login feature and maintain RTM | Youstina Atef | 3 | 3 | Done
| write SRS for Registration feature and maintain RTM | Youstina Atef | 3 | 3 | Done
| write SRS for Client feature and maintain RTM | Rana Saad | 4 | 5 | Done
| write SRS for Supplier feature and maintain RTM | Muhamed Mumtaz | 4 | 5 | Done
| Review for Login feature SRS | Rana Saad | 1 | 1 | Done
| Review for Registration feature SRS | Mariam Abdelmoneim | 1.5 | 2 | Done
| Review for Client feature SRS | Abdallah El-Karamany | 1 | 1 | Done
| Review for Supplier feature SRS | Mariam Abdelmoneim | 1.5 | 1 | Done
Test cases | Write test cases for Login feature SRS and maintain RTM | Abdallah El-Karamany | 3 | 2 | Done
| Write test cases for Registration feature SRS and maintain RTM | Rana Saad | 3 | 3 | Done
| Write test cases for Client feature SRS and maintain RTM | Youstina Atef | 3 | 3 | Done
| Write test cases for Supplier feature SRS and maintain RTM | Mariam Abdelmoneim | 4 | 2 | Done
| Review test cases for Login feature | Muhamed Mumtaz | 4 | 3 | Done
| Review test cases for Registration feature | Mariam Abdelmoneim | 1 | 1 | Done
| Review test cases for Client feature | Rana Saad | 1 | 1 | Done
| Review test cases for Supplier feature | youstina Atef | 1 | 1 | Done
UI Design | Sketch UI Design for Login page | Rana Saad | 4 |  | To do
| Sketch UI Design for Registration page | Youstina Atef | 3 | 4 | Done
| Sketch UI Design for Home page | Abdallah El-Karamany | 5 | 3 | Doing
| Sketch UI Design for Cart page | Mariam Abdelmoneim | 3 | 3 | Done
| Sketch UI Design for checkout page | Muhamed Mumtaz | 4 |  | To do
| Sketch UI Design for Order History page | Mariam Abdelmoneim | 4 | 3 | Done
| Review UI Design for Login page | Muhamed Mumtaz | 1 |  | To do
| Review UI Design for Registration page | Mariam Abdelmoneim | 1 |  | To do
| Review UI Design for Home page | Youstina Atef | 1 |  | To do
| Review UI Design for Cart page | Abdallah El-Karamany | 1 |  | To do
| Review UI Design for checkout page | Rana Saad | 1 |  | To do
| Review UI Design for Order History page | Abdallah El-Karamany | 1 |  | To do
Release 1 Comments | Update PMP according to comments | Abdallah El-Karamany | 3 | 2.5 | Done
| Update Risk Register according to comments | Abdallah El-Karamany | 2 | 1 | Done
| Create CIL | Abdallah El-Karamany | 1 | 1 | Done
| Update CRS Document according to comments | Abdallah El-Karamany | 1 | 1 | Done
Release 3 Planning |  | Abdallah El-Karamany | 2 |  | To do

## Status Report
Overall release work Status | Total Tasks 33 | Tasks in % | Total Time Spent
| 1 Doing | 3 % | 55.5 H
| 9 To do | 27.3 %
| 23 Done | 69.7

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 20 | 20
Mohamed Mumtaz | 14 | 13
Youstina Atef | 19 | 14
Rana Saad | 14 | 14
Mariam Abdelmoneim | 16 | 16
Total | 83 | 77