## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
UI Design | Create UI Design for Registration page | Youstina Atef | 4
| Create UI Design for Login page | Youstina Atef | 4
| Create UI Design for Client Home Page page | Rana Saad
| Create UI Design for Cart page | Mariam Abdelmoneam
| Create UI Design for CheckOut page | Rana Saad
| Create UI Design for OrderHistory page | Mariam Abdelmoneam
| Create UI Design for Supplier Home page | Muhamed Mumtaz
| Create UI Design for Supplier add new product page | Abdallah El-Karamany | 1 | 1 | Done
| Create UI Design for Supplier Update Product page | Muhamed Mumatz
| Create UI Design for Supplier Delete product | Abdallah El-Karamany | 1 | 1 | Done
| Review UI Design for Registration page | Mariam Abdelmoneam
| Review UI Design for Login page | Mariam Abdelmoneam
| Review UI Design for Client Home Page page | Muhamed Mumatz
| Review UI Design for Cart page | Youstina Atef | 1
| Review UI Design for CheckOut page | Muhamed Mumatz
| Review UI Design for OrderHistory page | Youstina Atef | 1
| Review UI Design for Supplier Home page | Abdallah El-Karamany | 0.5 | 0.5
| Review UI Design for Supplier add new product page | Rana Saad
| Review UI Design for Supplier Update Product page | Abdallah El-Karamany | 0.5 | 0.5
| Review UI Design for Supplier Delete product | Rana Saad
System Design | Create System Design for Registration page | Youstina Atef | 4 |  | Doing
| Create System Design for Login page | Youstina Atef | 4 |  | Doing
| Create System Design for Client Home Page page | Rana Saad
| Create System Design for Cart page | Mariam Abdelmoneam
| Create System Design for CheckOut page | Rana Saad
| Create System Design for OrderHistory page | Mariam Abdelmoneam
| Create System Design for Supplier Home page | Muhamed Mumtaz
| Create System Design for Supplier add new product page | Abdallah El-Karamany | 3 | 3 | Done
| Create System Design for Supplier Update Product page | Muhamed Mumatz
| Create System Design for Supplier Delete product | Abdallah El-Karamany | 3 | 3 | Done
| Review System Design for Registration page | Mariam Abdelmoneam
| Review System Design for Login page | Mariam Abdelmoneam
| Review System Design for Client Home Page page | Muhamed Mumatz
| Review System Design for Cart page | Youstina Atef | 1
| Review System Design for CheckOut page | Muhamed Mumatz
| Review System Design for OrderHistory page | Youstina Atef | 1
| Review System Design for Supplier Home page | Abdallah El-Karamany | 1
| Review System Design for Supplier add new product page | Rana Saad
| Review System Design for Supplier Update Product page | Abdallah El-Karamany | 1
| Review System Design for Supplier Delete product | Rana Saad
Release 2 Comments | Review Client SRS, TC and RTM | Youstina Atef
| Review Supplier SRS, TC and RTM | Mariam Abdelmoneam
| Review Registration SRS, TC and RTM | Mariam Abdelmoneam
| Review login SRS, TC and RTM | Abdallah El-Karamany | 1 | 1 | Done
Release 4 Planning |  | Abdallah El-Karamany | 3
Overall release % of work Status |  | Total Tasks 45 | Tasks in % |  | Total Time Spent
Doing
To do
Done

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 15 | 15
Mohamed Mumtaz | 10
Youstina Atef | 10 | 20
Rana Saad | 10
Mariam Abdelmoneim | 10
Total | 55