## WP
WP | Tasks | Team Member Assigned | Task estimated hours | Task Actual hours | Tasks status (in the WBS)
Test Case Execution | Test Case Execution for Registration Feature | Mariam | 2 | 2 | Done
| Test Case Execution for Login Feature | Rana | 2 | 2 | Done
| Test Case Execution for Supplier Feature | Youstina | 2 | 2 | Done
| Test Case Execution for Client Feature | Muhamed | 2 | 2 | Done
Release 5 Comments | Review and Update Registration feature | Mariam | 5 | 5 | Done
| Review and Update Login feature | Rana | 5 | 3 | Done
| Review and Update Supplier feature | Youstina | 5 | 5 | Done
| Review and Update Client feature | Muhamed | 5 | 4 | Done
| Bug Fixes | Abdallah | 3 | 2 | Done
PM Task | Test Strategy | Abdallah | 5 | 5 | Done
Overall release % of work Status |  | Total Tasks | 10 | Tasks in % | Total Time Spent
|  | Doing | 0 | 0% | 32
|  | To do | 0 | 0%
|  | Done | 10 | 100%

## Time Sheet
Team Members | Available Hours | Estimated Hours | Actual Hours
Abdallah El-Karamany | 10 | 8 | 7
Mohamed Mumtaz | 10 | 7 | 6
Youstina Atef | 10 | 7 | 7
Rana Saad | 10 | 7 | 5
Mariam Abdelmoneim | 10 | 7 | 7
Total | 50 | 36 | 32