## Sheet1
Risk ID | Risk Summary | Risk Category | Impact | Likehood | Risk Level | Mitigation Type | Mitigation Plan | Contingency Plan | Owner
R001 | Insufficient members in team. | Project Risk | Medium | High | High | Mitigate | Request additional resource from management with skills to match the project domain | - Distribute workload temporarily among current team members -Additional work hours beyond the standard schedule | Project Manager
R002 | Team member takes scheduled leave. | Project Risk | Medium | Medium | Medium | Mitigate | Review project schedule and adjust task deadlines for the team member who wants to take a leave. | - Extend working hours or work on weekends to compensate. - Request additional support from other teams or departments. | Project Manager
R003 | Limited budget may restrict the ability to purchase an appropriate domain name ,Hosting for the website. | Project Risk | High | High | High | Mitigate | -Explore budget-friendly domain registrars. - Use alternative which would be free. - Take advantage of promotions and discounts. - Consider registering a domain for a longer period to reduce cost. | -If budget remains tight, explore free subdomains for initial testing. - Prioritize the most critical aspect of the domain (e.g., brand recognition) and purchase a less expensive option. -Try to use college email to get free servers for hosting. | Project Manager
R004 | Website may be vulnerable to cyber-attacks due to weak security. | Product Risk | High | High | High | Mitigate | Use firewalls and anti-malware tools. | Back up the website regularly. | Project Manager
R005 | Slow website loading. | Product Risk | Medium | Low | Medium | Mitigate | - Optimize website code. -use medium quality images | Consider a website redesign for performance improvements. | Project Manager